## Ark1
| PLAN |  |  |  |  | DESIGN |  |  |  |  | BUILD |  |  |  |  | LAUNCH
| WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
PROJECT MANAGER | PROJECT MANAGEMENT, CUSTOMER CONTACT, PROPOSAL AND CONTRACT |  |  |  |  | PROJECT MANAGEMENT, CUSTOMER CONTACT |  |  |  |  | PROJECT MANAGEMENT, CUSTOMER CONTACT |  |  |  |  | PROJECT MANAGEMENT, CUSTOMER CONTACT
PROJECT MANAGER CONTENT MANAGER | REQUIREMENT MEETING | [17 empty] | MEETING WITH CLIENT + PRESENTATION
PROJECT MANAGER CONTENT MANAGER DESIGNER | IDENTIFYING GOALS AND RISKS PROJECT PLANNING |  | STRATEGIC PLANNING
DEVELOPER DESIGNER |  |  | RESEARCH |  | SITE OUTLINE | MOOD BOARD, STYLE TILES |  |  |  |  | WIREFRAMES | UX/UI PLANNING AND TESTING |  |  |  | UX/UI TESTING
CONTENT MANAGER |  |  | CONTENT PLANNING |  |  | CONTENT DEVELOPMENT
DEVELOPER | [7 empty] | SITE STRUCTURE (CODING, CSS, ETC)
PHOTOGRAPHER | [5 empty] | PHOTOSHOOT (WEBPAGE IMAGES) |  |  | PHOTOSHOOT (EMPLOYEE IMAGES)